# AOMI Kit QR Manager
Product Development Plan
30-Day MVP Roadmap

# 1. Executive Summary

AOMI Kit QR Manager is an internal web-based MVP designed to help AOMI sellers assign physical QR codes to skincare routine kits quickly, securely, and with minimal friction during the sales process.

The application will allow AOMI admins to manage products, diagnoses, routine types, predefined skincare routines, compatible product replacements, and QR tokens. Sellers/staff will use a simplified workflow to scan or manually enter a QR token, select the customer diagnosis, choose a predefined routine, replace products if needed, and assign the final routine to the QR code.

The main purpose of this MVP is not to build a complex dashboard or ecommerce system. The goal is to create a fast, reliable, and practical internal tool that supports the physical sales workflow and provides a clean API for the existing AOMI mobile app to retrieve routine data when the customer scans the QR code.

The project will be delivered as a 30-day MVP with a fixed project cost of $2,250.

# 2. MVP Objective

The MVP will deliver the following core capabilities:

- Admin can log in and manage the system.

- Seller/Staff can log in and use a simplified QR assignment flow.

- Admin can create, edit, deactivate, and manage products.

- Each product can support at least two uploaded reference images.

- Admin can manage diagnoses/needs, including combined diagnoses such as oily skin + pores or dark spots + sensitivity.

- Admin can manage routine types such as morning routine, night routine, and weekly routine.

- Admin can create and edit predefined skincare routine templates.

- Routine templates can include duration, routine type, diagnosis tags, steps, products, and usage instructions.

- Admin can define compatible product replacement rules by step/product type.

- Seller can select a diagnosis and routine from predefined options.

- Seller can replace products only with compatible alternatives.

- Seller can assign a physical QR token to the final routine.

- QR assignment can be done using a USB/Bluetooth scanner through an active input field.

- Manual QR code entry will be available as a backup.

- Admin can import QR tokens from CSV/Excel.

- Admin can generate QR token batches from the panel.

- Admin can export generated QR tokens as CSV/Excel.

- The system will validate QR tokens before assignment.

- The system will prevent duplicate, invalid, assigned, activated, voided, or replaced QR tokens from being incorrectly used.

- The backend will expose a documented REST API for the AOMI mobile app.

- The AOMI mobile app will be able to query a QR token and retrieve the assigned routine, products, instructions, duration, timing, and status.

- Basic logs will be stored for important admin/staff actions.

- The application will be deployed using cost-effective hosting and database services.

# 3. Product Vision

The AOMI Kit QR Manager should feel simple for sellers, even if the backend logic is structured and secure.

The seller-side experience should be fast:

Open assignment screen → scan or enter QR → select routine → replace products if needed → assign QR → finish.

The admin-side experience should be flexible:

Manage products → manage diagnoses → manage routine types → create predefined routines → manage compatible replacements → import/generate QR tokens → monitor QR statuses.

The MVP should give AOMI a strong operational foundation while keeping future expansion possible. Future phases may include deeper AOMI mobile app integrations, QR image/PDF label generation, advanced analytics, inventory, ecommerce, online orders, repurchase workflows, and more advanced recommendation logic.

# 4. Core Users and Roles

## 4.1 Admin

The Admin manages the internal setup and configuration.

Admin can:

- Manage products.

- Upload product images.

- Manage diagnoses/needs.

- Manage combined diagnoses.

- Manage routine types.

- Create and edit predefined routines.

- Define routine steps.

- Assign default products to routine steps.

- Define compatible replacement products.

- Import QR tokens from CSV/Excel.

- Generate QR token batches.

- Export QR tokens as CSV/Excel.

- View and manage QR token statuses.

- Void/disable QR tokens if needed.

- View basic logs.

- Access admin configuration screens.

## 4.2 Seller/Staff

The Seller/Staff role is designed for the point-of-sale workflow.

Seller/Staff can:

- Log in to the seller panel.

- Select customer diagnosis/need.

- Select a predefined skincare routine.

- Review routine steps and products.

- Replace products with compatible alternatives when required.

- Scan QR token using USB/Bluetooth scanner.

- Manually enter QR token as backup.

- Assign the finalized routine to the QR token.

- View assignment success/failure status.

- Avoid complex admin configuration screens.

# 5. Main Business Workflow

## 5.1 Admin Setup Flow

- Admin logs into the panel.

- Admin adds or imports product data.

- Admin uploads at least two reference images per product.

- Admin creates diagnosis/need categories.

- Admin creates routine types such as morning, night, and weekly.

- Admin creates predefined routine templates.

- Admin adds steps to each routine.

- Admin assigns default products to routine steps.

- Admin defines compatible replacement products.

- Admin imports or generates valid QR tokens.

- QR tokens are stored in the database with available status.

## 5.2 Seller QR Assignment Flow

- Seller logs into the panel.

- Seller opens the QR assignment workflow.

- Seller scans the physical QR token or enters the code manually.

- System validates the token.

- Seller selects the diagnosis/need.

- System shows matching predefined routines.

- Seller selects the routine.

- Seller reviews products and steps.

- Seller replaces products if needed.

- System only shows compatible replacements for each step.

- Seller confirms the final routine.

- System assigns the final package/routine to the QR token.

- QR token status changes from available to assigned.

- Seller sees success confirmation.

- Package is ready for customer use.

## 5.3 Customer Mobile App Flow

The AOMI mobile app is managed separately by the client’s internal team. This MVP will provide the backend API required for the mobile app.

Expected mobile app flow:

- Customer scans the QR code from the AOMI mobile app.

- Mobile app reads the unique QR token.

- Mobile app calls the backend API.

- Backend returns routine, products, instructions, duration, timing, and QR status.

- Mobile app shows preview to the customer.

- Customer confirms activation.

- Mobile app calls activation API.

- QR token status changes to activated.

- Routine is saved into the customer’s profile inside the AOMI app.

# 6. QR Token Workflow

The QR token workflow is a key part of the MVP.

## 6.1 QR Token Import

Admin can import QR tokens from CSV/Excel.

The imported file may include:

- QR token

- Batch name or batch reference

- Optional notes

- Optional status, if needed

The system will validate imported rows and prevent duplicates.

## 6.2 QR Token Generation

Admin can generate QR token batches directly from the panel.

Example generated formats:

- AOMI-KIT-8F7K92

- AOMI-KIT-3P9XQ1

- AOMI-KIT-L6M2RA

The system should prefer random unique tokens over simple sequential codes to reduce guessing, duplication, and manual mistakes.

## 6.3 QR Token Export

## 6.4 QR Token Validation

This exported file can be shared with the printing company or production team.

6.4 QR Token Validation

When a seller scans or manually enters a QR token, the system will check:

- Token follows the expected AOMI format.

- Token exists in the database.

- Token is not duplicated.

- Token is available for assignment.

- Token has not already been assigned.

- Token has not already been activated.

- Token is not voided/disabled.

- Token is not replaced.

## 6.5 QR Image and Printable PDF Scope

Actual QR image generation and printable PDF label sheet generation are not included in this MVP.

If the printing company later requires generated QR image files or PDF label sheets, this can be added as a future phase once the exact printing format is confirmed.

# 7. QR Token Statuses

The MVP will include basic token status management.

Recommended statuses:

- available: QR token exists and can be assigned.

- assigned: QR token has been assigned to a routine/package.

- activated: customer has activated the routine from the AOMI mobile app.

- voided/disabled: QR token should not be used due to error, damage, cancellation, or admin decision.

- replaced: QR token was replaced by another token.

Optional future statuses:

- packed: staff confirmed the package is ready.

- previewed: customer viewed routine preview but did not activate.

# 8. Routine and Diagnosis Logic

## 8.1 Diagnoses

Diagnoses/needs will be manageable from the admin panel.

Examples:

- Oily skin

- Pores

- Dark spots

- Sensitive skin

- Hydration

- Mixed skin

- Oily skin + pores

- Dark spots + sensitivity

- Hydration + pores

## 8.2 Combined Diagnoses

For the MVP, combined diagnoses should not automatically merge two separate routines.

Recommended MVP approach:

Admin creates routine templates and assigns one or more diagnosis tags to each routine.

Example:

Routine name: Oily Skin + Pores Morning Routine
Diagnosis tags: Oily skin, Pores
Routine type: Morning routine
Duration: 20 days
Steps: defined manually by admin

This approach keeps the system flexible without creating a complex automatic recommendation engine.

## 8.3 Routine Types

Routine types will be manageable from the admin panel.

Initial examples:

- Morning routine

- Night routine

- Weekly routine

Routine types can be edited or expanded later by the admin.

## 8.4 Routine Template Structure

Each predefined routine may include:

- Routine name

- Diagnosis/need tags

- Duration, such as 20 days or 30 days

- Routine type

- Number of steps

- Step type, such as cleanser, toner, serum, cream, sunscreen, exfoliant, or treatment

- Product assigned to each step

- Usage instructions for each step

- General routine instructions

- Compatible replacement products for each step

# 9. Product Management

Admin can manage product records.

Each product may include:

- Product name

- SKU or internal code

- Category

- Step/type compatibility

- Function/description

- Active/inactive status

- Front product image

- Secondary/reference image

- Compatible replacement rules

Products can be created manually from the admin panel.

A basic CSV/Excel import option will also be supported using an agreed format.

# 10. Product Replacement Logic

Replacement rules are important for seller speed and product safety.

Rules:

- Replacement options should be restricted by compatible step/type.

- A serum should not be replaced with sunscreen.

- A cleanser should not be replaced with cream.

- A sunscreen should not be replaced with toner.

- Seller should only see valid alternatives for the selected step.

- Replaced products should be saved as part of the final QR-assigned routine.

- The system should clearly show which product was replaced.

# 11. 30-Day Development Roadmap

## 11.1 Week 1 — Foundation, Architecture, and Core Setup

Key work:

- Set up project repository.

- Set up Next.js application.

- Set up Supabase/PostgreSQL database.

- Set up Supabase Storage for product images.

- Set up Vercel deployment foundation.

- Define database schema.

- Implement authentication foundation.

- Implement Admin and Seller/Staff role structure.

- Create initial dashboard layout.

- Create core navigation.

- Create first version of database tables.

Week 1 deliverables:

- Deployed application foundation.

- Login structure.

- Admin/Seller role separation.

- Database schema foundation.

- Initial dashboard shells.

- Project environment setup.

## 11.2 Week 2 — Admin Modules

Key work:

- Build product management.

- Build product image upload.

- Build diagnosis/needs management.

- Build routine type management.

- Build predefined routine creation/editing.

- Build routine step management.

- Build compatible replacement management.

- Build manual product/routine data entry screens.

Week 2 deliverables:

- Admin product CRUD.

- Product image upload.

- Diagnosis management.

- Routine type management.

- Routine template management.

- Compatible replacement configuration.

## 11.3 Week 3 — QR Token Workflow and Seller Flow

Key work:

- Build QR token import from CSV/Excel.

- Build QR token batch generation.

- Build QR token export as CSV/Excel.

- Implement QR token validation.

- Implement duplicate prevention.

- Implement basic token status management.

- Build seller QR assignment flow.

- Add USB/Bluetooth scanner support through active input field.

- Add manual QR entry fallback.

- Build routine selection flow.

- Build product replacement flow for seller.

Week 3 deliverables:

- QR import workflow.

- QR generation workflow.

- QR export workflow.

- QR validation rules.

- Seller assignment flow.

- Manual fallback entry.

- Product replacement during assignment.

## 11.4 Week 4 — API, Testing, Deployment, and Handover

Key work:

- Build REST API endpoints for AOMI mobile app integration.

- Create API documentation.

- Implement activation endpoint.

- Add basic logs for staff/admin actions.

- Test admin flow.

- Test seller flow.

- Test QR token assignment rules.

- Test duplicate/invalid/activated/voided token handling.

- Fix bugs.

- Deploy final MVP.

- Prepare handover instructions.

Week 4 deliverables:

- Documented REST API.

- Tested QR assignment workflow.

- Basic logs.

- Final deployed MVP.

- Handover instructions.

- Sample test data.

- Ready-to-use admin and seller flows.

# 12. Recommended Technology Stack

Frontend:

- Next.js

- TypeScript

- Tailwind CSS

- shadcn/ui or similar UI component system

Backend:

- Next.js API routes or server actions

- REST API for mobile app integration

Database:

- Supabase PostgreSQL

Storage:

- Supabase Storage for product images

Hosting:

- Vercel

Authentication:

- Simple login for Admin and Seller/Staff

- Role-based access control for MVP

Imports/Exports:

- CSV/Excel import for products, QR tokens, and replacement data using agreed formats

- CSV/Excel export for generated QR token batches

# 13. Included Scope

The MVP includes:

- Admin login and Seller/Staff login

- Admin dashboard

- Seller/Staff dashboard

- Product management

- Product image upload with at least two images per product

- Diagnosis/needs management

- Combined diagnosis support

- Routine type management

- Predefined routine creation and editing

- Routine steps

- Routine instructions

- Routine duration

- Product assignment to routine steps

- Compatible product replacement rules

- QR token import from CSV/Excel

- QR token batch generation

- QR token export as CSV/Excel

- QR token validation

- Duplicate prevention

- Basic token status management

- Seller QR assignment flow

- USB/Bluetooth scanner support through active input field

- Manual QR token entry fallback

- API endpoint for mobile app to retrieve QR/routine/product data

- API endpoint for routine activation

- API documentation for AOMI internal mobile app team

- Basic logs for important admin/staff actions

- Deployment setup

- Testing with sample QR tokens

- Basic handover instructions

# 14. Excluded Scope

The MVP does not include:

- AOMI mobile app development

- Ecommerce

- Full inventory/accounting system

- Advanced automatic skincare recommendation engine

- Automatic merging of multiple routines

- QR image generation

- Printable PDF label sheet generation

- QR label printing

- Advanced analytics/reporting

- Payment integrations

- Customer-facing web portal

- Full production-scale audit system

- Advanced multi-branch permission system

- Paid hosting/database costs if usage requires plan upgrades

# 15. Client Inputs Required

To start efficiently, AOMI should provide:

- Project-owned email account for GitHub, Vercel, Supabase, and related services

- Brand logo and basic design direction, if available

- Initial product sample data

- Sample product images

- Initial diagnosis list

- Initial routine type list

- Initial routine examples

- Product replacement rules, if available

- Sample QR tokens

- Preferred QR token format

- Internal mobile app API expectations, if already defined

- Any specific language preference for the admin/seller panel

# 16. Timeline Start Condition

The 30-day timeline will begin once:

- Fiverr order is active

- Project-owned account/email is available

- Required access is provided

- Initial sample data for products, routines, diagnoses, QR codes, and replacement rules is available

# 17. Acceptance Criteria

The MVP will be considered complete when:

- Admin can log in successfully.

- Seller/Staff can log in successfully.

- Admin can create and manage products.

- Admin can upload at least two product images.

- Admin can manage diagnoses and combined diagnosis tags.

- Admin can manage routine types.

- Admin can create and edit predefined routines.

- Admin can define routine steps and instructions.

- Admin can define compatible replacement products.

- Admin can import QR tokens from CSV/Excel.

- Admin can generate QR token batches.

- Admin can export QR tokens as CSV/Excel.

- System prevents duplicate QR tokens.

- System validates QR token format and database existence.

- Seller can scan or manually enter QR token.

- Seller can select diagnosis and routine.

- Seller can replace products only with compatible products.

- Seller can assign final routine to QR token.

- Assigned QR token status updates correctly.

- Activated/voided/replaced tokens cannot be assigned incorrectly.

- AOMI mobile app can query QR token through API.

- API returns routine, products, instructions, duration, timing, and status.

- API documentation is provided.

- Application is deployed.

- Basic handover instructions are provided.

# 18. End-of-MVP Outcome

At the end of the MVP, AOMI will have a functional internal web panel that allows admins to manage the routine system and sellers to assign QR codes quickly during the sales process.

The system will provide a clean backend foundation, secure QR token validation, routine assignment logic, product replacement control, and documented API integration for the AOMI mobile app.

The MVP will be ready for internal testing, seller workflow validation, and future expansion into additional AOMI ecosystem modules.